Web page Classification
Minor Project Schedule
&Progress report

---
Basic Coding
Completed
Deadline
10th September 2013
- Fetch data from given URL
- Parse HTML+JS+CSS file to get title and text
- Split Text Content into Words
- Remove stop words
- Apply Porter's Stemmer Algorithm for converting words to word root
- Count Frequency of Each words

---
Collection of training and testing samples
Work in progress
30th September 2013
- HTML+PHP interface for storing samples in database.
- Collect samples from search engines within following categories-200 records in each
  - Politics
  - Religion
  - Movies
  - Technology
  - Sports

---
Construction of Training set
10th October 2013
Not done yet
- Decide proper structure for database of training set samples
- Automation of training set construction

---
Implementation of Classification Algorithm
20th October 2013
- Implement Naive Bayes classification algorithm.
- Perform accuracy measurements

---
Implementation of GUI
31th October 2013
- Implement GUI using pygtk
- GUI should contain option for
  - Input url classification
  - Automatic training set construction

---
Debugging and Optimization
5th November 2013
- Test code for possible bugs
- Find optimal number of training set documents

---
END